INDEPENDENCE BLUE CROSS  ·  PROVIDER INFORMATION EXCHANGE (PIE)

2027 Priorities

ROM & Delivery Roadmap

Twelve business priorities with T-shirt-sized delivery effort, scope, dependencies, risks, and a 2027 roadmap.

| 12 Business Priorities | 3 XXL Programs (F2·F4·F7) | 4 Quarter Roadmap | 5–7 Senior Engineers, Full Year |
| --- | --- | --- | --- |

Confidential · For Internal Planning · July 2026

1.  Estimation Approach — T-Shirt Sizing

Each priority is estimated with a relative T-shirt size. The table below is the reference key that translates each size into an indicative developer-day range.

| T-Shirt Size | Estimated Dev-Days | Typical Scope |
| --- | --- | --- |
| S | ~5–15 dev-days | Small, isolated change to one component. |
| M | ~15–35 dev-days | Single component or flow, self-contained. |
| L | ~35–75 dev-days | Multi-component feature with integration. |
| XL | ~75–150 dev-days | Cross-cutting; multiple teams / systems touched. |
| XXL | ~150–300+ dev-days | Multi-quarter program; may need parallel teams. |

Ranges are indicative planning bands; actual effort is refined per priority during build planning.

The twelve priorities at a glance

| # | Priority | Size | Confidence |
| --- | --- | --- | --- |
| 1 | PDM Efficiency + PEAR Self-Service | XL | Med |
| 2 | Credentialing Enhancements | XXL | Mixed |
| 3 | Enhanced Case Management | L–XL | Med |
| 4 | Full Provider Data Versioning | XXL | Med / High-risk |
| 5 | Cred + PDM Integration | L | Med |
| 6 | Inventory Management & Reporting | L–XL | Low–Med |
| 7 | Mass Data Load Capabilities | XXL | Med |
| 8 | Lexis Nexis + Compliance | XL | LN Med / Comp Low |
| 9 | Stabilization & Tech Debt | L–XL | Med |
| 10 | Re-Cred PSV Add/Remove Location → PDM Routing | XL | Med |
| 11 | FHNatic — Provider Forms External Portal | XL | Low–Med |
| 12 | POMS Replacement — Multi-Request PDM | XL | Low–Med |

Portfolio size mix

XXL (3): F2 Credentialing, F4 Data Versioning, F7 Mass Data Loads — multi-quarter programs. F2 and F4 each exceed twice the floor of the XXL band and should be funded in phases, not as single items.

XL (5): F1 PDM + PEAR, F8 Lexis Nexis + Compliance, F10 Re-Cred PSV Location → PDM, F11 FHNatic Provider Forms, F12 POMS Replacement.

L–XL (3): F3 Case Management, F6 Inventory & Reporting, F9 Stabilization.

L (1): F5 Cred + PDM Integration.

Priorities 11–12 (FHNatic, POMS) are carried in from the Oct 2025 'FHNatic / POMS / Mass Grid' estimate (originally in story points; shown here mapped to T-shirt sizes). That document's Mass Grid initiative is already represented by Priority 7 (Mass Data Load Capabilities).

2.  Priority Detail

Priority 1 — PDM Efficiency + PEAR Provider Self-Service

| T-SHIRT SIZE XL | CONFIDENCE Medium |
| --- | --- |

What we're delivering

Balanced internal PDM efficiency + external PEAR self-service.

PEAR: providers add / term locations, networks, and demographics themselves.

PDM: self-serve simple field edits to cut the admin-ticket queue.

How we'll build it (high-level TDD)

PEAR edits update provider records directly — there is no QC review step for PEAR.

Harden community FLS / security and inline validation for provider-facing writes.

Extend existing PEAR OmniScripts + DataRaptors rather than rebuild.

Top risk:  Because PEAR writes apply directly (no QC gate), inline validation and a full audit trail are essential to protect data integrity. Only 15 of 192 custom components are community-enabled today, so provider-facing screens carry an enablement cost.

Reuse / dependency:  Internal PDM bulk edits can leverage the F7 async engine; PEAR updates apply directly.

Priority 2 — Credentialing Enhancements — Tiles, CAQH Documents & Agentic AI

| T-SHIRT SIZE XXL | CONFIDENCE Mixed (Tile High / CAQH Low–Med / Agentic Med–Low) |
| --- | --- |

What we're delivering

The 5 core credentialing flows re-platformed to the tile experience — a codebase audit counts ~108 steps in those flows (not the ~55 tiles originally assumed).

Retrieve real CAQH document files — not just structured data.

Agentic AI: Phase 0 foundation + 2 pilot agents (human-in-the-loop).

How we'll build it (high-level TDD)

Shared tile + session framework across all flows (autosave, resume-anywhere).

CAQH document API to Salesforce Files + audit linkage.

Einstein Trust Layer, RAG grounding, human-in-loop, and an eval harness.

Top risk:  This is a multi-team program, not one feature — the wider credentialing family is 45 OmniScripts / 304 steps, so the '5 flows' boundary must be named before funding. CAQH connectivity already exists (44 CAQH Apex classes + a CAQH named credential); it is the document entitlement that is unverified.

Reuse / dependency:  The tile framework is reused across all flows and by the mass-update grid (F7).

Priority 3 — Enhanced Case Management

| T-SHIRT SIZE L–XL | CONFIDENCE Medium |
| --- | --- |

What we're delivering

Smart + configurable case routing and assignment.

Fix the duplicate-QC-case defect; fix queue & owner-change permissions.

Exception / hold tracking + in-case tracker, worklists, and SLA aging.

How we'll build it (high-level TDD)

Idempotent case creation to kill duplicates; skill + workload assignment engine.

Hold / exception model with reason codes and re-entry rules.

SLA aging alerts + supervisor worklist views.

Top risk:  Touches the shared review IP write path — meaningful regression surface across credentialing. There are 14 queues but zero assignment rules today, so all routing is code-driven and the configurable engine is genuinely net-new.

Reuse / dependency:  Routing & worklists are reused by F5 (shared views) and F6 (leadership inventory).

Priority 4 — Full Provider Data Versioning

| T-SHIRT SIZE XXL | CONFIDENCE Medium (High Risk) |
| --- | --- |

What we're delivering

Effective-dated versioning across the 42 provider objects that are actually written today (the earlier '~30' undercounted).

Drivers: compliance, point-in-time history, future & back-dated changes.

Pinned-current model with version-up / version-down.

How we'll build it (high-level TDD)

Version state-machine: pinned-current + version down/up + back-date + natural-key error-out.

Point-in-time query API. Phase by tier: Tier 1 = the 14 highest-traffic objects, which carry ~80% of the write path.

Heavy regression harness to protect existing write paths. A partial head start exists — 596 fields are already history-tracked across 53 objects.

Top risk:  Regression blast radius measured at 478 write-path Load DataMappers and 236 DML-performing Apex classes across 42 objects — larger than previously stated. 7 business pre-conditions remain open. Strongly recommend funding Tier 1 only in 2027.

Reuse / dependency:  The versioned write model underpins F5 (no re-entry), F6 (history feeds), and F8 (terminations).

Priority 5 — Cred + PDM Integration

| T-SHIRT SIZE L | CONFIDENCE Medium |
| --- | --- |

What we're delivering

Automated cred to PDM handoff — no manual re-entry.

Shared cross-team views + a unified data model.

One-way direction; covers ReCred + Initial Cred.

How we'll build it (high-level TDD)

Generalize RCAT eligibility to PDM push.

Cross-team worklist + shared record views.

Cred to PDM field mapping + de-duplication.

Top risk:  Overlaps F3 & F4 — booked net-new to avoid double-counting shared foundations.

Reuse / dependency:  Builds directly on F3 worklists and the F4 versioned model. Sequence after both.

Priority 6 — Inventory Management & Reporting

| T-SHIRT SIZE L–XL | CONFIDENCE Low–Medium |
| --- | --- |

What we're delivering

OOTB reports + dashboards for leadership and operations.

Integrity / operational feed automation.

Work-inventory & backlog visibility for leadership.

How we'll build it (high-level TDD)

Field-change extract engine for granular deltas.

Per-feed parity validation against source systems.

Throughput / backlog / aging dashboards.

Top risk:  The integrity-feed count is unknown — a discovery inventory gates the upper end of the range. Reporting is near-greenfield today (5 reports and 1 dashboard exist), though 45 report types give a usable foundation.

Reuse / dependency:  Field-history source comes from F4; worklists / inventory from F3.

Priority 7 — Mass Data Load Capabilities

| T-SHIRT SIZE XXL | CONFIDENCE Medium (Foundational) |
| --- | --- |

What we're delivering

Build the reusable async mass-load engine.

Refactor 3 high-volume flows onto the engine.

7+ distinct mass operations (CSV / bulk + QC routing).

How we'll build it (high-level TDD)

PRM_AsyncJob engine: orchestrator, batch, dead-letter queue, progress LWC.

Per-operation: payload validator + batch + QC routing.

Metadata-driven sequencing, halt-on-failure, and retry.

Top risk:  Engine is confirmed not built (the async job objects do not exist), though there is a head start: the service base and utility classes are deployed, the async constants are already defined, and 71 batch classes exist as precedent. The number of operations dominates effort — confirm the exact 7+ list.

Reuse / dependency:  The engine is consumed by F1, F5, and F8. Build this first.

Priority 8 — Lexis Nexis Integration + Compliance Mandates

| T-SHIRT SIZE XL | CONFIDENCE LN Med / Compliance Low |
| --- | --- |

What we're delivering

LexisNexis inbound: phone update, directory suppression.

Practitioner terminations + roster attestation.

Compliance mandates: a discovery spike + reserved envelope.

How we'll build it (high-level TDD)

Reuse PRM_AsyncProcess staging to Platform Event to batch to outbound.

Termination cascade (Full / Non-Par / Last-Man-Standing).

Compliance sized after the discovery spike.

Top risk:  The termination cascade is a large hidden chunk; compliance scope is undefined until the spike. A LexisNexis feature toggle is already wired into 10 Integration Procedures in the address / PAR pipeline, but no LexisNexis credential exists — so the API call itself is still net-new.

Reuse / dependency:  Uses the F4 versioned model for terminations and the F7 async engine for feeds.

Priority 9 — System Stabilization & Technical Debt Reduction

| T-SHIRT SIZE L–XL | CONFIDENCE Medium (Continuous) |
| --- | --- |

What we're delivering

Burn down ~40 documented defects / debt items / manual data scripts.

Reserve a ~15–20% annual capacity envelope.

Root-cause fixes for recurring failure classes.

How we'll build it (high-level TDD)

Triage & register; prioritized burn-down.

Regression tests around every fix.

Exclude items owned by F3 / F4 / F7 to avoid double-counting.

Top risk:  A continuous cost that competes directly with feature capacity — must be reserved, not assumed.

Reuse / dependency:  Runs across all four quarters alongside every other workstream.

Priority 10 — Re-Cred PSV Add/Remove Location → Auto-Route to PDM

| T-SHIRT SIZE XL | CONFIDENCE Medium |
| --- | --- |

What we're delivering

Re-enable add / remove of a practice location during the Re-Cred PSV process — today it is paused and the Re-Cred team emails PDM manually.

On a location change, automatically create and route a case to the PDM / Re-Cred PDA (RCAT) team — replacing the manual email.

Scope a location removal to the single affiliation being acted on, not every practitioner at the location.

How we'll build it (high-level TDD)

Deploy the async practice-location processor so high-volume CAQH location sets no longer time out (shares the F7 engine).

Fix the Re-Cred PDA Update P0 defects: location-removal mass-termination (Bug 1216121), QC Errors-Found table leak (Bug 1216120), and terminated-location 'Required Fields Missing'.

Route the location change to PDM via Case / Case Manager (RCAT pickup) and harden partial-write rollback so a mid-chain failure leaves no orphans.

Top risk:  Paused in production for high-volume timeouts and P0 data-integrity defects; a safe resume is gated on the async processor + defect fixes (per the 2026-06-08 readiness audit). Confirm the fixes are the active org versions before lifting the email-only hold.

Reuse / dependency:  Async processor overlaps F7; effective-date / termination fixes overlap F4; QC case routing overlaps F3 — book largely net of those.

Priority 11 — FHNatic — Provider Forms External Portal Exposure

| T-SHIRT SIZE XL | CONFIDENCE Low–Medium |
| --- | --- |

What we're delivering

Expose four existing internal provider forms on the external provider portal for self-service: PAR Form, Non-Par Registration, Provider Change Request, and Ancillary Cred Guided Flow.

Providers submit their own requests directly instead of internal teams keying them in.

Per-form external UI/UX, data validation, portal integration, and security.

How we'll build it (high-level TDD)

Update and expose each existing internal guided flow externally — reuse, don't rebuild.

Make the ~17 custom components used by these four forms community-ready, then re-test each form in the external context.

External-user UI/UX adjustments, field validation, and community security / FLS per form.

Top risk:  Re-sized upward from the original 32–52 story points. The provider portal already exists, which helps — but only 15 of 192 custom components are community-enabled today, and these four forms are the highest-churn assets in the org (one is on version 117). Community enablement and regression on those components were not in the original per-form figure.

Reuse / dependency:  Shares the external-portal foundation with F1 (PEAR self-service) and reuses the existing internal guided flows — book net of F1's portal work.

Priority 12 — POMS Replacement — Multi-Request PDM Submission

| T-SHIRT SIZE XL | CONFIDENCE Low–Medium |
| --- | --- |

What we're delivering

Replace legacy POMS: let Network Coordinators submit multiple PDM update requests in a single action.

New UI for multi-request submission plus a processing workflow that creates / updates many records from one submission.

Reuse the existing PDM Manual Updates guided flow for individual record processing.

How we'll build it (high-level TDD)

New multi-request intake UI + submission workflow.

Bulk data-handling framework to fan one submission out into many record updates (leverage the F7 async engine).

Reuse the PDM Manual Updates guided flow per record.

Top risk:  Original estimate 80–120 story points. The PDM Manual Update family being reused is large (7 guided flows, ~99 steps), so the per-record reuse is real but the multi-request wrapper is the work. The bulk-handling framework overlaps F7 — net-new is lower if F7's async engine lands first.

Reuse / dependency:  Strong overlap with F7 (bulk framework) and the existing PDM Manual Updates guided flow. Sequence after F7; book net of the engine.

3.  Shared Foundations — Read Before Summing

Several priorities depend on the same building blocks. Each foundation is booked once with its primary owner; consumers reuse it. Sequencing foundation-first turns overlap into savings.

| Shared foundation | Primary owner | Also consumed by |
| --- | --- | --- |
| Async / bulk engine (PRM_AsyncJob__c) | F7 | F1 (PDM bulk edits), F5, F10 (PSV location processor), F12 (POMS bulk) |
| External-submission QC routing (Case / CM / CDM + CMA) | F7 | F3, F5, F8, F10 (note: PEAR is direct, no QC) |
| External provider portal foundation | F1 | F11 (FHNatic forms) |
| PDM Manual Updates guided flow | existing | F12 (POMS per-record processing) |
| Versioned / effective-dated write model | F4 | F5 (no re-entry), F6 (history feeds), F8 (termination) |
| Analyst worklists / routing | F3 | F5 (shared views), F6 (leadership inventory) |
| Field-history data source | F4 | F6 (integrity feeds) |
| Tile + session UI framework | F2 | F7 mass-update grid cells |

Build foundations first: F7 async engine and F4 versioning are the two spines.

Net-new already deducted: F5 is booked net-of-overlap; F9 excludes items owned by F3/F4/F7.

Sequencing saves effort: F7→F1, F4→(F5/F6/F8), F3→(F5/F6) reuse work already paid for.

4.  2027 Delivery Timeline & Sequencing

| Workstream | Q1 · Foundations | Q2 · Build | Q3 · Scale | Q4 · Harden & Cut Over |
| --- | --- | --- | --- | --- |
| Async & Mass Load | F7 engine build | F7 first ops + F1 PEAR | F7 remaining mass ops | — |
| Versioning | F4 architecture | F4 Tier-1 objects | F4 Tier-2 / 3 objects | F4 parity + cutover |
| Credentialing | — | F2 tile framework (parallel team) | F2 CAQH docs + flow migrations | F2 Agentic pilots go-live |
| Case / Integ / Report | F3 routing + defect fix | F10 Re-Cred PSV→PDM (defects + async) | F5 integration + F6 reports | F6 integrity feeds + dashboards |
| Feeds & Compliance | — | F8 LexisNexis on engine | F8 terminations + spike | F8 compliance build |
| External Portal / POMS | — | F11 FHNatic forms (reuse F1 portal) | F12 POMS multi-request (on F7 engine) | — |
| Stabilization (F9) | Continuous ~15–20% reserved capacity across all four quarters |  |  |  |

Q1 — Foundations: Stand up F7 async engine, start F4 architecture and F3 routing.

Q2–Q3 — Build & Scale: F1 + F8 on the engine; F4 object tiers; F2 tiles (parallel team); F5/F6 as F3/F4 land.

Q4 — Harden & Cut Over: Versioning parity + cutover, Agentic pilots (post F2), and compliance build (post spike).

5.  Portfolio Sizing & Resource Mix

Portfolio size profile

Size mix: 3 XXL + 5 XL + 3 L–XL + 1 L across the twelve priorities.

Heavy hitters: the three XXL programs (F2, F4, F7) dominate the portfolio and drive the timeline.

Team & resource mix

Staffing: ~5–7 senior engineers sustained across the full year.

Roles: Apex / Platform, OmniStudio, LWC, QA, Data / Integration, PM / BA.

Parallelism: F2, F4, and F7 are three concurrent multi-quarter programs.

Read the sizing as indicative.  F9 is a reserved capacity envelope and F5 is booked net-new; several priorities share foundations. Sequence foundations first — don't sum the sizes naively. See the sizing key in Section 1 for the T-shirt to dev-day translation.

Capacity reality check

Translating the twelve T-shirt sizes through the Section 1 key gives a portfolio of roughly 2,130–3,020 developer-days, or about 9–13 developer-years. A team of 5–7 senior engineers supplies roughly 1,150–1,610 developer-days in a year. The portfolio as scoped is therefore about twice what the stated team can deliver in 2027.

Option A — Increase staffing to roughly 9–13 engineers.

Option B — Phase the portfolio: deliver F7 (engine + first operations), F4 Tier 1, F3, F1, F10 and F2 Phase 1, with the F9 envelope. That slice fits 5–7 engineers.

Option C — Cut scope outright — defer F5, F6, F8, F11 and F12 to 2028.

The single highest-leverage scope decision is F4: limiting versioning to the 14 highest-traffic objects captures roughly 80% of the write path for about half the cost.

6.  Risks & Open Questions

Top program risks

Portfolio exceeds capacity: the twelve priorities total roughly twice what 5–7 engineers can deliver in 2027. Phasing or additional staffing is required — see the capacity reality check in Section 5.

Versioning blast radius (F4): 478 write-path Load DataMappers and 236 DML-performing Apex classes across 42 objects, plus 7 open pre-conditions.

Credentialing scope boundary (F2): the credentialing family is 45 guided flows / 304 steps; the core 5 flows alone are ~108 steps against the ~55 tiles originally assumed.

Community component gap (F1 / F11): only 15 of 192 custom components are community-enabled, so any provider-facing screen carries an enablement and re-test cost.

CAQH document API (F2): connectivity exists, but document entitlement is unverified.

Compliance scope (F8): undefined until the discovery spike.

Re-Cred PSV route paused (F10): resume is gated on the async location processor + P0 data-integrity defects (Bug 1216121 / 1216120, terminated-location) per the 2026-06-08 audit.

Fixed-cost work: OmniStudio publish, UAT, shadow parity, and integration testing do not compress.

Open questions carried forward

| Feature | Open question |
| --- | --- |
| F2 | Name the exact step list for the '5 flows' — is it ~55 tiles or the ~108 steps the audit counts? Confirm CAQH document entitlement; all-5-flows in one year needs parallel teams. |
| F4 | Approve Tier 1 = the 14 highest-traffic objects (~80% of the write path); resolve the 7 pre-conditions + natural keys. Also confirm the history-tracking limit on Individual Application, which shows 61 tracked fields. |
| F5 | Confirm cred tracks (ReCred / Initial / PAR) + outcome-to-PDM matrix. |
| F6 | Run the integrity-feed discovery inventory (count unknown). |
| F7 | Confirm the exact 7+ mass-operation list. |
| F8 | Define the compliance mandate(s) + deadline. |
| F9 | Confirm reserved % (15–20% proposed) and the double-count boundary. |
| F10 | Resume scope — all recred locations vs low-volume first; confirm the async processor + P0 defect fixes are deployed before lifting the email-only hold. |
| F11 | Which of the ~17 components used by the four forms are already community-safe, and how much of F1's portal foundation is reusable? |
| F12 | Confirm the multi-request volume and whether POMS's bulk framework is fully covered by F7's async engine (to avoid rebuild). |
| All | Provide real sprint velocity — these sizes are structure-based, and the repo history is a one-month snapshot that offers no velocity signal. |

7.  Next Steps & Decisions

Decisions to make now

1. Confirm the per-feature scope.

2. Decide: fund F2 / F4 / F7 as parallel programs, or phase them across the year.

3. Approve the reserved stabilization capacity (~15–20%).

Discovery spikes to schedule

CAQH document API entitlement & access.

Integrity-feed inventory (count & parity rules).

Compliance mandate(s) definition & deadline.

Mass-operation catalog — confirm the exact 7+ list.

Each priority has a standalone TDD + estimation doc in requirements/2027_ROM_TDD/.